## Overview
AGRIWATER – Project Monitoring Tool
Smart water management for climate-resilient Mediterranean agriculture
Status as of
Project information
Acronym |  |  |  | Grant Agreement
Type of Action |  |  |  | Call
Total Budget |  |  |  | Call Topic
EU Contribution |  |  |  | Partners |  | 6
Timeline
Start |  |  |  | End
Duration |  |  |  | Current Month
Time Elapsed |  |  |  | Remaining
Current Period |  |  |  | Next Report Due
Deliverables |  |  |  | Milestones
Total |  |  |  | Total
Submitted / accepted |  |  |  | Achieved
Overdue |  |  |  | Overdue
Due by end of month |  |  |  | Due by end of month
Due within 3 months |  |  |  | Due within 3 months
Due within 6 months |  |  |  | Due within 6 months
Completion |  |  |  | Completion
Next meeting
Date |  |  |  | Days |  | =IFERROR(INDEX(M_Days,MATCH($D$28,M_Date,0))&"","")
Description |  | =IFERROR(INDEX(M_Description,MATCH($D$28,M_Date,0))&"","") |  | Place |  | =IFERROR(INDEX(M_Place,MATCH($D$28,M_Date,0))&"","")
Participants |  | =IFERROR(INDEX(M_Participants,MATCH($D$28,M_Date,0))&"","") |  | Host |  | =IFERROR(INDEX(M_Host,MATCH($D$28,M_Date,0))&"","")
Work packages
WP | Title |  | Leader | Start | End | Deliverables | Submitted | Progress | Overdue
WP1 | Project management and coordination |  | UCN | 1 | 36
WP2 | Field requirements and pilot design |  | AGROLAB | 1 | 18
WP3 | Sensor network and data platform |  | DATAWISE | 4 | 30
WP4 | Pilots and impact assessment |  | HYDRA | 10 | 36
WP5 | Communication, dissemination and exploitation |  | GREENCOM | 1 | 36
Click a WP code to open its sheet. Deliverable and milestone status is kept in the 'Upcoming_MilestonesDeliverables' sheet.

## Gantt
AGRIWATER – Gantt chart
[5 empty] | Year 1 (Jan 2026 – Dec 2026) | [11 empty] | Year 2 (Jan 2027 – Dec 2027) | [11 empty] | Year 3 (Jan 2028 – Dec 2028) | [11 empty] | Year 4 (Jan 2029 – Feb 2029)
WP | Task | Task Name | Start | End | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
1 | T1.1 | Administrative and financial coordination | 1 | 36 | MS1 |  | D1.1
| T1.2 | Quality assurance and risk management | 1 | 36
| T1.3 | Data management plan | 1 | 36 | [5 empty] | D1.2 | [23 empty] | D1.3
2 | T2.1 | Stakeholder needs analysis | 1 | 8 | [7 empty] | D2.1, MS2
| T2.2 | Pilot site selection and baseline | 3 | 12 | [11 empty] | D2.2
| T2.3 | Pilot protocols | 9 | 18 | [17 empty] | D2.3
3 | T3.1 | Low-cost soil moisture sensor network | 4 | 20 | [13 empty] | D3.1, MS3
| T3.2 | Irrigation decision-support platform | 8 | 30 | [19 empty] | D3.2 | [9 empty] | D3.3, MS5
4 | T4.1 | Pilot deployment | 10 | 30 | [17 empty] | MS4 | [5 empty] | D4.1
| T4.2 | Environmental and economic impact assessment | 18 | 36 | [35 empty] | D4.2
5 | T5.1 | Communication and dissemination plan | 1 | 36 |  |  | D5.1 | D5.2
| T5.2 | Farmer engagement and training | 6 | 36 | [23 empty] | D5.3
| T5.3 | Exploitation and business planning | 12 | 36 | [35 empty] | D5.4, MS6
Reporting periods |  |  |  |  | RP1 (M1–M18) | [17 empty] | RP2 (M19–M36)
Periodic reports (preparation / due) | [23 empty] | RP1 | [17 empty] | RP2
Meetings and events |  |  |  |  | ● | [5 empty] | ● |  |  | ● |  |  | ● |  |  |  |  | ● |  |  | ● | [8 empty] | ● | [5 empty] | ●
Legend
| D1.1 | Deliverable due in that month (hover for the title)
| MS1 | Milestone due in that month
| RP1 | Periodic report due; light orange = report preparation
| ● | Meeting or event (hover for details)
| M1 | Current month is highlighted in red
Note on G6: MS1: Kick-off meeting held
Note on I6: D1.1: Project handbook
Note on L8: D1.2: Data management plan
Note on AJ8: D1.3: Updated data management plan
Note on N9: D2.1: Stakeholder requirements report MS2: User requirements agreed
Note on R10: D2.2: Pilot site baseline assessment
Note on X11: D2.3: Pilot protocols
Note on T12: D3.1: Sensor network prototype MS3: Sensor prototype validated in the lab
Note on Z13: D3.2: Decision-support platform v1
Note on AJ13: D3.3: Decision-support platform final release MS5: Platform released
Note on X14: MS4: All pilots operational
Note on AD14: D4.1: Pilot deployment report
Note on AP15: D4.2: Impact assessment report
Note on I16: D5.1: Communication and dissemination plan
Note on J16: D5.2: Project website and visual identity
Note on AD17: D5.3: Training materials for farmers
Note on AP18: D5.4: Exploitation and business plan MS6: Final event held
Note on Z21: RP1 periodic report due (M20)
Note on AR21: RP2 periodic report due (M38)
Note on G22: Kick-off meeting 20/01/2026 – 21/01/2026 Nicosia Host: UCN All partners, Project Officer
Note on M22: Steering committee 08/07/2026 Online Host: UCN WP leaders
Note on P22: General assembly 14/10/2026 – 15/10/2026 Madrid Host: AGROLAB All partners
Note on S22: Steering committee 13/01/2027 Online Host: UCN WP leaders
Note on X22: General assembly 09/06/2027 – 10/06/2027 Athens Host: HYDRA All partners
Note on AA22: Farmer field day 22/09/2027 Brussels Host: EUFARM Farmers, stakeholders
Note on AJ22: General assembly 14/06/2028 – 15/06/2028 Munich Host: DATAWISE All partners
Note on AP22: Final event 05/12/2028 – 06/12/2028 Rome Host: GREENCOM All partners, stakeholders

## Planning
Year | Year 1 (Jan 2026 – Dec 2026) | [11 empty] | Year 2 (Jan 2027 – Dec 2027) | [11 empty] | Year 3 (Jan 2028 – Dec 2028) | [11 empty] | Year 4 (Jan 2029 – Feb 2029)
Month | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 | 35 | 36 | 37 | 38
Date
Deliverables due |  |  | D1.1 | D5.2 |  | D1.2 |  | D2.1 |  |  |  | D2.2 |  | D3.1 |  |  |  | D2.3 |  | D3.2 |  |  |  | D4.1 | [5 empty] | D1.3 | [5 empty] | D4.2
|  |  | D5.1 | [20 empty] | D5.3 | [5 empty] | D3.3 | [5 empty] | D5.4
Milestones | MS1 | [6 empty] | MS2 | [5 empty] | MS3 |  |  |  | MS4 | [11 empty] | MS5 | [5 empty] | MS6
General Assembly | Kick-off meeting | [8 empty] | General assembly | [7 empty] | General assembly | [11 empty] | General assembly
Steering Committee | [6 empty] | Steering committee | [5 empty] | Steering committee
Events | [20 empty] | Farmer field day | [14 empty] | Final event
Reporting | [17 empty] | RP1 ends |  | RP1 report due | [15 empty] | RP2 ends |  | RP2 report due
Note on D4: D1.1: Project handbook
Note on E4: D5.2: Project website and visual identity
Note on G4: D1.2: Data management plan
Note on I4: D2.1: Stakeholder requirements report
Note on M4: D2.2: Pilot site baseline assessment
Note on O4: D3.1: Sensor network prototype
Note on S4: D2.3: Pilot protocols
Note on U4: D3.2: Decision-support platform v1
Note on Y4: D4.1: Pilot deployment report
Note on AE4: D1.3: Updated data management plan
Note on AK4: D4.2: Impact assessment report
Note on D5: D5.1: Communication and dissemination plan
Note on Y5: D5.3: Training materials for farmers
Note on AE5: D3.3: Decision-support platform final release
Note on AK5: D5.4: Exploitation and business plan
Note on B6: MS1: Kick-off meeting held
Note on I6: MS2: User requirements agreed
Note on O6: MS3: Sensor prototype validated in the lab
Note on S6: MS4: All pilots operational
Note on AE6: MS5: Platform released
Note on AK6: MS6: Final event held
Note on B7: Kick-off meeting 20/01/2026 – 21/01/2026 Nicosia Host: UCN All partners, Project Officer
Note on K7: General assembly 14/10/2026 – 15/10/2026 Madrid Host: AGROLAB All partners
Note on S7: General assembly 09/06/2027 – 10/06/2027 Athens Host: HYDRA All partners
Note on AE7: General assembly 14/06/2028 – 15/06/2028 Munich Host: DATAWISE All partners
Note on H8: Steering committee 08/07/2026 Online Host: UCN WP leaders
Note on N8: Steering committee 13/01/2027 Online Host: UCN WP leaders
Note on V9: Farmer field day 22/09/2027 Brussels Host: EUFARM Farmers, stakeholders
Note on AK9: Final event 05/12/2028 – 06/12/2028 Rome Host: GREENCOM All partners, stakeholders
Note on S10: End of reporting period RP1
Note on U10: Periodic report for RP1 due
Note on AK10: End of reporting period RP2
Note on AM10: Periodic report for RP2 due

## Upcoming_MilestonesDeliverables
WP | DELIVERABLE | NAME | PARTNER | TYPE | DISSEMINATION | MONTH | DUE DATE | STATUS | EC STATUS | SUBMITTED ON | COMMENTS
WP1 | D1.1 | Project handbook | UCN | R | SEN | 3
WP5 | D5.1 | Communication and dissemination plan | GREENCOM | R | PU | 3
WP5 | D5.2 | Project website and visual identity | GREENCOM | DEC | PU | 4
WP1 | D1.2 | Data management plan | UCN | DMP | PU | 6
WP2 | D2.1 | Stakeholder requirements report | AGROLAB | R | PU | 8
WP2 | D2.2 | Pilot site baseline assessment | AGROLAB | R | SEN | 12
WP3 | D3.1 | Sensor network prototype | DATAWISE | DEM | PU | 14
WP2 | D2.3 | Pilot protocols | HYDRA | R | PU | 18
WP3 | D3.2 | Decision-support platform v1 | DATAWISE | OTHER | PU | 20
WP4 | D4.1 | Pilot deployment report | HYDRA | R | PU | 24
WP5 | D5.3 | Training materials for farmers | EUFARM | R | PU | 24
WP1 | D1.3 | Updated data management plan | UCN | DMP | PU | 30
WP3 | D3.3 | Decision-support platform final release | DATAWISE | OTHER | PU | 30
WP4 | D4.2 | Impact assessment report | HYDRA | R | PU | 36
WP5 | D5.4 | Exploitation and business plan | UCN | R | SEN | 36
WP | MILESTONE | NAME | LEADER | MEANS OF VERIFICATION |  | MONTH | DUE DATE | STATUS | EC STATUS | ACHIEVED ON | COMMENTS
WP1 | MS1 | Kick-off meeting held | UCN | Meeting minutes |  | 1
WP2 | MS2 | User requirements agreed | AGROLAB | D2.1 submitted |  | 8
WP3 | MS3 | Sensor prototype validated in the lab | DATAWISE | Validation report |  | 14
WP4 | MS4 | All pilots operational | HYDRA | Pilot status report |  | 18
WP3 | MS5 | Platform released | DATAWISE | D3.3 submitted |  | 30
WP5 | MS6 | Final event held | GREENCOM | Event agenda and attendance |  | 36
Formulas:
DUE DATE = IF([MONTH]="","",EOMONTH(ProjectStartDate,[MONTH]-1))

## WP1
AGRIWATER · Work Package 1
WP# | 1 |  | WP Leader |  | Deliverables |  | Submitted / Accepted |  | Progress
UCN
WP Title
Project management and coordination
[5 empty] | Due within 3 months |  | Due within 6 months |  | Overdue
[5 empty] | =COUNTIFS(D_WP,"WP1",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),3),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO") |  | =COUNTIFS(D_WP,"WP1",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),6),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO")
| Start | 1
| End | 36
Deliverable and milestone status is updated in the 'Upcoming_MilestonesDeliverables' sheet.
Deliverables
Deliverable No | Deliverable Title |  |  | Responsible Partner | Type | Dissemin. Level | Due | Due Date | Status | Comments
D1.1 | Project handbook |  |  | UCN | R | SEN | 3
D1.2 | Data management plan |  |  | UCN | DMP | PU | 6
D1.3 | Updated data management plan |  |  | UCN | DMP | PU | 30
Milestones
Milestone No | Milestone Title |  |  | Leader | Means of Verification |  | Due | Due Date | Status | Comments
MS1 | Kick-off meeting held |  |  | UCN | Meeting minutes |  | 1
Formulas:
Due Date = IF([Submitted / Accepted]="","",EOMONTH(ProjectStartDate,[Submitted / Accepted]-1))

## WP1_Tasks
WP1 – Project management and coordination
M1–M36 · Leader: UCN
TASK | DURATION | SUBTASK | MILESTONES | DELIVERABLES | DEADLINE | STATUS | PLANNING | LEAD | PARTICIPANTS | RESP. PERSONNEL | COMMENTS
T1.1: Administrative and financial coordination | M1–M36 | Organise the kick-off meeting and set up the governance bodies | MS1 | n/a | 1 | ONGOING |  | UCN | All | UCN
|  | Prepare the project handbook with internal procedures | n/a | D1.1 | 3 | ONGOING |  |  |  | UCN
|  | Coordinate periodic technical and financial reporting | n/a | n/a | 20 | ONGOING |  |  |  | UCN
T1.2: Quality assurance and risk management | M1–M36 |  | n/a | n/a |  | ONGOING |  | UCN | HYDRA
T1.3: Data management plan | M1–M36 | Deliverable D1.2: Data management plan | n/a | D1.2 | 6 | ONGOING |  | UCN | DATAWISE | UCN
|  | Deliverable D1.3: Updated data management plan | n/a | D1.3 | 30 | ONGOING |  |  |  | UCN

## WP2
AGRIWATER · Work Package 2
WP# | 2 |  | WP Leader |  | Deliverables |  | Submitted / Accepted |  | Progress
AGROLAB
WP Title
Field requirements and pilot design
[5 empty] | Due within 3 months |  | Due within 6 months |  | Overdue
[5 empty] | =COUNTIFS(D_WP,"WP2",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),3),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO") |  | =COUNTIFS(D_WP,"WP2",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),6),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO")
| Start | 1
| End | 18
Deliverable and milestone status is updated in the 'Upcoming_MilestonesDeliverables' sheet.
Deliverables
Deliverable No | Deliverable Title |  |  | Responsible Partner | Type | Dissemin. Level | Due | Due Date | Status | Comments
D2.1 | Stakeholder requirements report |  |  | AGROLAB | R | PU | 8
D2.2 | Pilot site baseline assessment |  |  | AGROLAB | R | SEN | 12
D2.3 | Pilot protocols |  |  | HYDRA | R | PU | 18
Milestones
Milestone No | Milestone Title |  |  | Leader | Means of Verification |  | Due | Due Date | Status | Comments
MS2 | User requirements agreed |  |  | AGROLAB | D2.1 submitted |  | 8
Formulas:
Due Date = IF([Submitted / Accepted]="","",EOMONTH(ProjectStartDate,[Submitted / Accepted]-1))

## WP2_Tasks
WP2 – Field requirements and pilot design
M1–M18 · Leader: AGROLAB
TASK | DURATION | SUBTASK | MILESTONES | DELIVERABLES | DEADLINE | STATUS | PLANNING | LEAD | PARTICIPANTS | RESP. PERSONNEL | COMMENTS
T2.1: Stakeholder needs analysis | M1–M8 | Run interviews and workshops with farmers in the pilot regions | n/a | n/a | 6 | ONGOING |  | AGROLAB | EUFARM, UCN | EUFARM
|  | Publish the stakeholder requirements report | MS2 | D2.1 | 8 | ONGOING |  |  |  | AGROLAB
T2.2: Pilot site selection and baseline | M3–M12 | Deliverable D2.2: Pilot site baseline assessment | n/a | D2.2 | 12 | ONGOING |  | AGROLAB | HYDRA | AGROLAB
T2.3: Pilot protocols | M9–M18 | Deliverable D2.3: Pilot protocols | n/a | D2.3 | 18 | ONGOING |  | HYDRA | AGROLAB, EUFARM | HYDRA

## WP3
AGRIWATER · Work Package 3
WP# | 3 |  | WP Leader |  | Deliverables |  | Submitted / Accepted |  | Progress
DATAWISE
WP Title
Sensor network and data platform
[5 empty] | Due within 3 months |  | Due within 6 months |  | Overdue
[5 empty] | =COUNTIFS(D_WP,"WP3",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),3),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO") |  | =COUNTIFS(D_WP,"WP3",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),6),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO")
| Start | 4
| End | 30
Deliverable and milestone status is updated in the 'Upcoming_MilestonesDeliverables' sheet.
Deliverables
Deliverable No | Deliverable Title |  |  | Responsible Partner | Type | Dissemin. Level | Due | Due Date | Status | Comments
D3.1 | Sensor network prototype |  |  | DATAWISE | DEM | PU | 14
D3.2 | Decision-support platform v1 |  |  | DATAWISE | OTHER | PU | 20
D3.3 | Decision-support platform final release |  |  | DATAWISE | OTHER | PU | 30
Milestones
Milestone No | Milestone Title |  |  | Leader | Means of Verification |  | Due | Due Date | Status | Comments
MS3 | Sensor prototype validated in the lab |  |  | DATAWISE | Validation report |  | 14
MS5 | Platform released |  |  | DATAWISE | D3.3 submitted |  | 30
Formulas:
Due Date = IF([Submitted / Accepted]="","",EOMONTH(ProjectStartDate,[Submitted / Accepted]-1))

## WP3_Tasks
WP3 – Sensor network and data platform
M4–M30 · Leader: DATAWISE
TASK | DURATION | SUBTASK | MILESTONES | DELIVERABLES | DEADLINE | STATUS | PLANNING | LEAD | PARTICIPANTS | RESP. PERSONNEL | COMMENTS
T3.1: Low-cost soil moisture sensor network | M4–M20 | Deliverable D3.1: Sensor network prototype | n/a | D3.1 | 14 | ONGOING |  | DATAWISE | UCN | DATAWISE
|  | Milestone MS3: Sensor prototype validated in the lab | MS3 | n/a | 14 | ONGOING |  |  |  | DATAWISE
T3.2: Irrigation decision-support platform | M8–M30 | Deliverable D3.2: Decision-support platform v1 | n/a | D3.2 | 20 | ONGOING |  | DATAWISE | HYDRA | DATAWISE
|  | Deliverable D3.3: Decision-support platform final release | n/a | D3.3 | 30 | ONGOING |  |  |  | DATAWISE
|  | Milestone MS5: Platform released | MS5 | n/a | 30 | ONGOING |  |  |  | DATAWISE

## WP4
AGRIWATER · Work Package 4
WP# | 4 |  | WP Leader |  | Deliverables |  | Submitted / Accepted |  | Progress
HYDRA
WP Title
Pilots and impact assessment
[5 empty] | Due within 3 months |  | Due within 6 months |  | Overdue
[5 empty] | =COUNTIFS(D_WP,"WP4",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),3),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO") |  | =COUNTIFS(D_WP,"WP4",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),6),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO")
| Start | 10
| End | 36
Deliverable and milestone status is updated in the 'Upcoming_MilestonesDeliverables' sheet.
Deliverables
Deliverable No | Deliverable Title |  |  | Responsible Partner | Type | Dissemin. Level | Due | Due Date | Status | Comments
D4.1 | Pilot deployment report |  |  | HYDRA | R | PU | 24
D4.2 | Impact assessment report |  |  | HYDRA | R | PU | 36
Milestones
Milestone No | Milestone Title |  |  | Leader | Means of Verification |  | Due | Due Date | Status | Comments
MS4 | All pilots operational |  |  | HYDRA | Pilot status report |  | 18
Formulas:
Due Date = IF([Submitted / Accepted]="","",EOMONTH(ProjectStartDate,[Submitted / Accepted]-1))

## WP4_Tasks
WP4 – Pilots and impact assessment
M10–M36 · Leader: HYDRA
TASK | DURATION | SUBTASK | MILESTONES | DELIVERABLES | DEADLINE | STATUS | PLANNING | LEAD | PARTICIPANTS | RESP. PERSONNEL | COMMENTS
T4.1: Pilot deployment | M10–M30 | Deliverable D4.1: Pilot deployment report | n/a | D4.1 | 24 | NOT STARTED |  | HYDRA | AGROLAB, EUFARM | HYDRA
|  | Milestone MS4: All pilots operational | MS4 | n/a | 18 | NOT STARTED |  |  |  | HYDRA
T4.2: Environmental and economic impact assessment | M18–M36 | Deliverable D4.2: Impact assessment report | n/a | D4.2 | 36 | NOT STARTED |  | HYDRA | UCN | HYDRA

## WP5
AGRIWATER · Work Package 5
WP# | 5 |  | WP Leader |  | Deliverables |  | Submitted / Accepted |  | Progress
GREENCOM
WP Title
Communication, dissemination and exploitation
[5 empty] | Due within 3 months |  | Due within 6 months |  | Overdue
[5 empty] | =COUNTIFS(D_WP,"WP5",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),3),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO") |  | =COUNTIFS(D_WP,"WP5",D_Due,">="&TODAY(),D_Due,"<="&EOMONTH(TODAY(),6),D_Status,"<>Submitted to PO",D_Status,"<>Accepted by PO")
| Start | 1
| End | 36
Deliverable and milestone status is updated in the 'Upcoming_MilestonesDeliverables' sheet.
Deliverables
Deliverable No | Deliverable Title |  |  | Responsible Partner | Type | Dissemin. Level | Due | Due Date | Status | Comments
D5.1 | Communication and dissemination plan |  |  | GREENCOM | R | PU | 3
D5.2 | Project website and visual identity |  |  | GREENCOM | DEC | PU | 4
D5.3 | Training materials for farmers |  |  | EUFARM | R | PU | 24
D5.4 | Exploitation and business plan |  |  | UCN | R | SEN | 36
Milestones
Milestone No | Milestone Title |  |  | Leader | Means of Verification |  | Due | Due Date | Status | Comments
MS6 | Final event held |  |  | GREENCOM | Event agenda and attendance |  | 36
Formulas:
Due Date = IF([Submitted / Accepted]="","",EOMONTH(ProjectStartDate,[Submitted / Accepted]-1))

## WP5_Tasks
WP5 – Communication, dissemination and exploitation
M1–M36 · Leader: GREENCOM
TASK | DURATION | SUBTASK | MILESTONES | DELIVERABLES | DEADLINE | STATUS | PLANNING | LEAD | PARTICIPANTS | RESP. PERSONNEL | COMMENTS
T5.1: Communication and dissemination plan | M1–M36 | Deliverable D5.1: Communication and dissemination plan | n/a | D5.1 | 3 | ONGOING |  | GREENCOM | All | GREENCOM
|  | Deliverable D5.2: Project website and visual identity | n/a | D5.2 | 4 | ONGOING |  |  |  | GREENCOM
T5.2: Farmer engagement and training | M6–M36 | Deliverable D5.3: Training materials for farmers | n/a | D5.3 | 24 | ONGOING |  | EUFARM | GREENCOM | EUFARM
T5.3: Exploitation and business planning | M12–M36 | Deliverable D5.4: Exploitation and business plan | n/a | D5.4 | 36 | NOT STARTED |  | UCN | DATAWISE | UCN
|  | Milestone MS6: Final event held | MS6 | n/a | 36 | NOT STARTED |  |  |  | GREENCOM

## Risk Management
Critical risks & risk management strategy
Risk No | Description | WP No(s) | Likelihood | Severity | Proposed Mitigation Measures | Status | RP1 Update | RP2 Update
1 | Delays in the delivery of sensor hardware | WP3, WP4 | Medium | High | Order components early and qualify a second supplier. | Open
2 | Low engagement of farmers in the pilots | WP2, WP4, WP5 | Medium | Medium | Involve farmer associations from the start and offer training. | Open
3 | Drought or extreme weather affecting the pilot season | WP4 | Low | High | Run pilots over two seasons and in several regions. | Open
4 | Delay in submitting deliverables | WP1, WP2, WP3, WP4, WP5 | Low | Medium | Internal deadlines one month before the contractual due date. | Open

## KPIs
Key Performance Indicators
KPI No | Description | Work Package | Target | RP1 Update | RP2 Update
1.1 | Water savings in pilot farms | WP4 | >= 20%
1.2 | Farmers using the decision-support platform | WP3, WP4 | >= 150
2.1 | Farmers and advisors trained | WP5 | >= 500
Communication and dissemination KPIs
No | Channel | Target Groups | KPI | RP1 Update | RP2 Update
1 | Project website | All | 1500 visitors per month
2 | Social media | Farmers, public | 8 posts per month
3 | Scientific publications | Academic community | 6 open access

## Partners
Partners and contacts
No | Name | Short Name | Country | Active | Joined | Left | WPs Led | Contact Person | Email | Telephone | Role / Responsible For
1 | University of Coastal Nations | UCN | CY | Yes |  |  | WP1
2 | Hydra Analytics Ltd | HYDRA | GR | Yes |  |  | WP4
3 | Agronomy Research Laboratory | AGROLAB | ES | Yes |  |  | WP2
4 | European Farmers Network | EUFARM | BE | Yes
5 | DataWise Solutions GmbH | DATAWISE | DE | Yes |  |  | WP3
6 | GreenCom Communication Agency | GREENCOM | IT | Yes |  |  | WP5

## Meetings
Meetings and events
ID | Type | Date | End Date | Days | Month | Place | Host | Description | Participants | Minutes / Notes
1 | General Assembly | 2026-01-20 |  | 2 |  | Nicosia | UCN | Kick-off meeting | All partners, Project Officer
2 | Steering Committee | 2026-07-08 |  | 1 |  | Online | UCN | Steering committee | WP leaders
3 | General Assembly | 2026-10-14 |  | 2 |  | Madrid | AGROLAB | General assembly | All partners
4 | Steering Committee | 2027-01-13 |  | 1 |  | Online | UCN | Steering committee | WP leaders
5 | General Assembly | 2027-06-09 |  | 2 |  | Athens | HYDRA | General assembly | All partners
6 | Events | 2027-09-22 |  | 1 |  | Brussels | EUFARM | Farmer field day | Farmers, stakeholders
7 | General Assembly | 2028-06-14 |  | 2 |  | Munich | DATAWISE | General assembly | All partners
8 | Events | 2028-12-05 |  | 2 |  | Rome | GREENCOM | Final event | All partners, stakeholders

## Inconsistencies
Inconsistencies found in the project data
No | Issue | Where | Resolution / Comments | Resolved
No inconsistencies were detected when the monitoring tool was generated.

## configInfo
Project information |  | Calculated values (do not edit) |  | Reporting Periods
Duration (mo) | 36 | Project End |  | ID | Start (month) | End (month) | Report Due (month)
Project Start | 2026-01-01 | Current Month (project month, 0 = not started) |  | RP1 | 1 | 18 | 20
Project Acronym | AGRIWATER | Max Deliverables in one month | 2 | RP2 | 19 | 36 | 38
Project Title | Smart water management for climate-resilient Mediterranean agriculture | Max Tasks in one WP | 3
Grant Agreement No | 101000001 | First Day of the Current Month
Total Budget | 2498750 | Duration (full years)
EU Contribution | 2498750 | Duration (months after the last full year)
Call | HORIZON-CL6-2025-01 | Next Periodic Report Due (month)
Call Topic | HORIZON-CL6-2025-01-FARM2FORK-01 | Generated On | 2026-09-17
Action | HORIZON Research and Innovation Actions

## configDataVal
Deliverable Status | Milestone Status | Dissemination Level | Deliverable Types | EC Status | Task Status | Risk Level | Risk Status | Yes / No
Drafting Begun | Achieved | PU | R | Pending | NOT STARTED | Low | Open | Yes
Waiting Feedback | Partially Achieved | SEN | REPORT | Accepted | ONGOING | Medium | Monitoring | No
Submitted to PO | Not Achieved | CO | DEM | Revision Requested | COMPLETED | High | Occurred
Accepted by PO | Issue | CI | DEC | Rejected | DELAYED |  | Closed
Rejected by PO |  | R-UE/EU-R | DATA |  | ON HOLD
On Hold |  | C-UE/EU-C | DMP
Issue |  | S-UE/EU-S | ORDP
Other (See Comment) |  |  | ETHICS
SECURITY
OTHER