## Instructions
Project Monitoring Tool – input template
1. Project information | Fill in the 'configInfo' sheet. Acronym, start date and duration are required.
2. Work plan | Fill in the tables of the 'configProject' sheet: work packages, milestones, tasks, deliverables, partners, reporting periods and meetings. Add rows at the bottom of a table as needed; empty rows are ignored.
3. Optional details | The 'configPlanning' sheet holds optional tables: subtasks (activities per task), risks, KPIs and communication KPIs. Leave them empty if you do not need them. Columns with a grey header are optional too.
4. Months | Months are counted from the project start: M1 is the first month of the project. Type them as numbers (6) or as M6.
5. Codes | Work packages: 1 or WP1. Tasks: T1.1. Deliverables: D1.1. Milestones: 1 or MS1. Partners are referred to by their short name.
6. Generate | Save the file and upload it in the web app. It is checked for errors and inconsistencies before the monitoring tool is generated.
Coming soon | Filling in this template automatically from the Grant Agreement (PDF) with AI.

## configInfo
Project information
Duration (mo) * | Total project duration in months, e.g. 36
Project Start * | First day of the project, e.g. 01/09/2026
Project Acronym * | Short project name, e.g. CaBRIOH
Project Title | Full project title
Grant Agreement No | Grant agreement number, e.g. 101290977
Total Budget | Total budget in EUR
EU Contribution | EU contribution in EUR
Call | e.g. HORIZON-INFRA-2025-01
Call Topic | e.g. HORIZON-INFRA-2025-01-DEV-01
Action | e.g. HORIZON Coordination and Support Actions
* required

## configProject
Work Packages |  |  |  |  | Milestones | [6 empty] | Tasks | [6 empty] | Deliverables | [7 empty] | Partners | [6 empty] | Reporting Periods |  |  |  | Meetings
WP | Title | Leader | Ms | Mf | MS | Title | Month | WP | Leader | Verification | Task | Task | Description | WP | Start | End | Lead | Participants | D | Title | WP | Responsible Partner | Deliverable Type | Dissemination Level | Delivery Date | Task | ID | Name | Shortname | Country | Active | StartedAt | EndedAt | ID | Reporting Period Start | Due | Reporting Period End | ID | Date | Num of Days | Place | Host | Description | Participants | Month | Meeting End | Type
Note on A2: Work package number, e.g. 1 (required)
Note on B2: Work package title
Note on C2: Short name of the leading partner
Note on D2: Start month, e.g. 1
Note on E2: End month, e.g. 36
Note on G2: Milestone number, e.g. 1 or MS1 (required)
Note on H2: Milestone title
Note on I2: Due month, e.g. 3
Note on J2: Work package number
Note on K2: Short name of the responsible partner
Note on L2: Means of verification
Note on M2: Optional: related task (e.g. T1.1), used to place it in the Gantt chart (optional)
Note on O2: Task number, e.g. T1.1 (required)
Note on P2: Task title
Note on Q2: Work package number (taken from the task number when empty)
Note on R2: Start month
Note on S2: End month
Note on T2: Optional: short name of the leading partner (optional)
Note on U2: Optional: participating partners, comma separated (optional)
Note on W2: Deliverable number, e.g. D1.1 (required)
Note on X2: Deliverable title
Note on Y2: Work package number (taken from the deliverable number when empty)
Note on Z2: Short name of the responsible partner
Note on AA2: e.g. R, REPORT, DEM, DEC, DATA, OTHER
Note on AB2: e.g. PU, SEN, CO
Note on AC2: Due month number, e.g. 6
Note on AD2: Optional: task producing it (e.g. T1.1), used to place it in the Gantt chart (optional)
Note on AF2: Partner number
Note on AG2: Full legal name
Note on AH2: Short name used in the other tables (required)
Note on AI2: Country
Note on AJ2: TRUE or FALSE
Note on AK2: Month the partner joined (empty = from the start)
Note on AL2: Month the partner left (empty = until the end)
Note on AN2: Period number, e.g. 1
Note on AO2: First month of the period, e.g. 1 (required)
Note on AP2: Month the periodic report is due, e.g. 20
Note on AQ2: Last month of the period, e.g. 18 (required)
Note on AS2: Meeting number
Note on AT2: First day of the meeting
Note on AU2: Number of days
Note on AV2: City or 'Online'
Note on AW2: Hosting partner
Note on AX2: e.g. Kick-off meeting
Note on AY2: Who attends
Note on AZ2: Calculated from the date, can be left empty
Note on BA2: Calculated from the date, can be left empty
Note on BB2: Optional: grouping in the Planning sheet, e.g. General Assembly (optional)

## configPlanning
Subtasks (optional) | [5 empty] | Risks (optional) | [5 empty] | KPIs (optional) |  |  |  | Communication KPIs (optional)
Task | Subtask | Milestones | Deliverables | Deadline | Responsible | ID | Description | WP | Likelihood | Severity | Mitigation | ID | Description | WP | Target | Channel | Target Groups | KPI
Note on A2: Task number, e.g. T1.1 (required)
Note on B2: Description of the activity
Note on C2: Related milestones, e.g. MS1
Note on D2: Related deliverables, e.g. D1.1
Note on E2: Deadline month, e.g. 6
Note on F2: Responsible partner or person
Note on H2: Risk number
Note on I2: Description of the risk (required)
Note on J2: Work packages involved, e.g. WP1, WP2
Note on K2: Low, Medium or High
Note on L2: Low, Medium or High
Note on M2: Proposed risk-mitigation measures
Note on O2: KPI number, e.g. 1.1
Note on P2: Description of the indicator (required)
Note on Q2: Work package(s)
Note on R2: Target value
Note on T2: Communication channel (required)
Note on U2: Audience
Note on V2: Target value

## configDataVal (hidden)
DeliverableTypes | DisseminationLevel | RiskLevel | TrueFalse
R | PU | Low | TRUE
REPORT | SEN | Medium | FALSE
DEM | CO | High
DEC | CI
DATA | R-UE/EU-R
DMP | C-UE/EU-C
ORDP | S-UE/EU-S
ETHICS
SECURITY
OTHER