## Instructions
Project Monitoring Tool – input template
1. Project information | Fill in the 'configInfo' sheet. Acronym, start date and duration are required.
2. Work plan | Fill in the tables of the 'configProject' sheet: work packages, milestones, tasks, deliverables, partners, reporting periods and meetings. Add rows at the bottom of a table as needed; empty rows are ignored.
3. Optional details | The 'configPlanning' sheet holds optional tables: subtasks (activities per task), risks, KPIs and communication KPIs. Leave them empty if you do not need them. Columns with a grey header are optional too.
4. Months | Months are counted from the project start: M1 is the first month of the project. Type them as numbers (6) or as M6.
5. Codes | Work packages: 1 or WP1. Tasks: T1.1. Deliverables: D1.1. Milestones: 1 or MS1. Partners are referred to by their short name.
6. Generate | Save the file and upload it in the web app. It is checked for errors and inconsistencies before the monitoring tool is generated.
Coming soon | Filling in this template automatically from the Grant Agreement (PDF) with AI.

## configInfo
Project information
Duration (mo) * | 36 | Total project duration in months, e.g. 36
Project Start * | 2026-01-01 | First day of the project, e.g. 01/09/2026
Project Acronym * | AGRIWATER | Short project name, e.g. CaBRIOH
Project Title | Smart water management for climate-resilient Mediterranean agriculture | Full project title
Grant Agreement No | 101000001 | Grant agreement number, e.g. 101290977
Total Budget | 2498750 | Total budget in EUR
EU Contribution | 2498750 | EU contribution in EUR
Call | HORIZON-CL6-2025-01 | e.g. HORIZON-INFRA-2025-01
Call Topic | HORIZON-CL6-2025-01-FARM2FORK-01 | e.g. HORIZON-INFRA-2025-01-DEV-01
Action | HORIZON Research and Innovation Actions | e.g. HORIZON Coordination and Support Actions
* required

## configProject
Work Packages |  |  |  |  | Milestones | [6 empty] | Tasks | [6 empty] | Deliverables | [7 empty] | Partners | [6 empty] | Reporting Periods |  |  |  | Meetings
WP | Title | Leader | Ms | Mf | MS | Title | Month | WP | Leader | Verification | Task | Task | Description | WP | Start | End | Lead | Participants | D | Title | WP | Responsible Partner | Deliverable Type | Dissemination Level | Delivery Date | Task | ID | Name | Shortname | Country | Active | StartedAt | EndedAt | ID | Reporting Period Start | Due | Reporting Period End | ID | Date | Num of Days | Place | Host | Description | Participants | Month | Meeting End | Type
1 | Project management and coordination | UCN | 1 | 36 | 1 | Kick-off meeting held | 1 | 1 | UCN | Meeting minutes |  | T1.1 | Administrative and financial coordination | 1 | 1 | 36 | UCN | All | D1.1 | Project handbook | 1 | UCN | R | SEN | 3 | T1.1 | 1 | University of Coastal Nations | UCN | CY | TRUE |  |  | 1 | 1 | 20 | 18 | 1 | 2026-01-20 | 2 | Nicosia | UCN | Kick-off meeting | All partners, Project Officer |  | 2026-01-21 | General Assembly
2 | Field requirements and pilot design | AGROLAB | 1 | 18 | 2 | User requirements agreed | 8 | 2 | AGROLAB | D2.1 submitted |  | T1.2 | Quality assurance and risk management | 1 | 1 | 36 | UCN | HYDRA | D5.1 | Communication and dissemination plan | 5 | GREENCOM | R | PU | 3 |  | 2 | Hydra Analytics Ltd | HYDRA | GR | TRUE |  |  | 2 | 19 | 38 | 36 | 2 | 2026-07-08 | 1 | Online | UCN | Steering committee | WP leaders |  | 2026-07-08 | Steering Committee
3 | Sensor network and data platform | DATAWISE | 4 | 30 | 3 | Sensor prototype validated in the lab | 14 | 3 | DATAWISE | Validation report |  | T1.3 | Data management plan | 1 | 1 | 36 | UCN | DATAWISE | D5.2 | Project website and visual identity | 5 | GREENCOM | DEC | PU | 4 |  | 3 | Agronomy Research Laboratory | AGROLAB | ES | TRUE | [6 empty] | 3 | 2026-10-14 | 2 | Madrid | AGROLAB | General assembly | All partners |  | 2026-10-15 | General Assembly
4 | Pilots and impact assessment | HYDRA | 10 | 36 | 4 | All pilots operational | 18 | 4 | HYDRA | Pilot status report |  | T2.1 | Stakeholder needs analysis | 2 | 1 | 8 | AGROLAB | EUFARM, UCN | D1.2 | Data management plan | 1 | UCN | DMP | PU | 6 | T1.3 | 4 | European Farmers Network | EUFARM | BE | TRUE | [6 empty] | 4 | 2027-01-13 | 1 | Online | UCN | Steering committee | WP leaders |  | 2027-01-13 | Steering Committee
5 | Communication, dissemination and exploitation | GREENCOM | 1 | 36 | 5 | Platform released | 30 | 3 | DATAWISE | D3.3 submitted |  | T2.2 | Pilot site selection and baseline | 2 | 3 | 12 | AGROLAB | HYDRA | D2.1 | Stakeholder requirements report | 2 | AGROLAB | R | PU | 8 |  | 5 | DataWise Solutions GmbH | DATAWISE | DE | TRUE | [6 empty] | 5 | 2027-06-09 | 2 | Athens | HYDRA | General assembly | All partners |  | 2027-06-10 | General Assembly
[5 empty] | 6 | Final event held | 36 | 5 | GREENCOM | Event agenda and attendance |  | T2.3 | Pilot protocols | 2 | 9 | 18 | HYDRA | AGROLAB, EUFARM | D2.2 | Pilot site baseline assessment | 2 | AGROLAB | R | SEN | 12 |  | 6 | GreenCom Communication Agency | GREENCOM | IT | TRUE | [6 empty] | 6 | 2027-09-22 | 1 | Brussels | EUFARM | Farmer field day | Farmers, stakeholders |  | 2027-09-22 | Events
[12 empty] | T3.1 | Low-cost soil moisture sensor network | 3 | 4 | 20 | DATAWISE | UCN | D3.1 | Sensor network prototype | 3 | DATAWISE | DEM | PU | 14 | [12 empty] | 7 | 2028-06-14 | 2 | Munich | DATAWISE | General assembly | All partners |  | 2028-06-15 | General Assembly
[12 empty] | T3.2 | Irrigation decision-support platform | 3 | 8 | 30 | DATAWISE | HYDRA | D2.3 | Pilot protocols | 2 | HYDRA | R | PU | 18 | [12 empty] | 8 | 2028-12-05 | 2 | Rome | GREENCOM | Final event | All partners, stakeholders |  | 2028-12-06 | Events
[12 empty] | T4.1 | Pilot deployment | 4 | 10 | 30 | HYDRA | AGROLAB, EUFARM | D3.2 | Decision-support platform v1 | 3 | DATAWISE | OTHER | PU | 20
[12 empty] | T4.2 | Environmental and economic impact assessment | 4 | 18 | 36 | HYDRA | UCN | D4.1 | Pilot deployment report | 4 | HYDRA | R | PU | 24
[12 empty] | T5.1 | Communication and dissemination plan | 5 | 1 | 36 | GREENCOM | All | D5.3 | Training materials for farmers | 5 | EUFARM | R | PU | 24
[12 empty] | T5.2 | Farmer engagement and training | 5 | 6 | 36 | EUFARM | GREENCOM | D1.3 | Updated data management plan | 1 | UCN | DMP | PU | 30 | T1.3
[12 empty] | T5.3 | Exploitation and business planning | 5 | 12 | 36 | UCN | DATAWISE | D3.3 | Decision-support platform final release | 3 | DATAWISE | OTHER | PU | 30
[19 empty] | D4.2 | Impact assessment report | 4 | HYDRA | R | PU | 36
[19 empty] | D5.4 | Exploitation and business plan | 5 | UCN | R | SEN | 36
Note on A2: Work package number, e.g. 1 (required)
Note on B2: Work package title
Note on C2: Short name of the leading partner
Note on D2: Start month, e.g. 1
Note on E2: End month, e.g. 36
Note on G2: Milestone number, e.g. 1 or MS1 (required)
Note on H2: Milestone title
Note on I2: Due month, e.g. 3
Note on J2: Work package number
Note on K2: Short name of the responsible partner
Note on L2: Means of verification
Note on M2: Optional: related task (e.g. T1.1), used to place it in the Gantt chart (optional)
Note on O2: Task number, e.g. T1.1 (required)
Note on P2: Task title
Note on Q2: Work package number (taken from the task number when empty)
Note on R2: Start month
Note on S2: End month
Note on T2: Optional: short name of the leading partner (optional)
Note on U2: Optional: participating partners, comma separated (optional)
Note on W2: Deliverable number, e.g. D1.1 (required)
Note on X2: Deliverable title
Note on Y2: Work package number (taken from the deliverable number when empty)
Note on Z2: Short name of the responsible partner
Note on AA2: e.g. R, REPORT, DEM, DEC, DATA, OTHER
Note on AB2: e.g. PU, SEN, CO
Note on AC2: Due month number, e.g. 6
Note on AD2: Optional: task producing it (e.g. T1.1), used to place it in the Gantt chart (optional)
Note on AF2: Partner number
Note on AG2: Full legal name
Note on AH2: Short name used in the other tables (required)
Note on AI2: Country
Note on AJ2: TRUE or FALSE
Note on AK2: Month the partner joined (empty = from the start)
Note on AL2: Month the partner left (empty = until the end)
Note on AN2: Period number, e.g. 1
Note on AO2: First month of the period, e.g. 1 (required)
Note on AP2: Month the periodic report is due, e.g. 20
Note on AQ2: Last month of the period, e.g. 18 (required)
Note on AS2: Meeting number
Note on AT2: First day of the meeting
Note on AU2: Number of days
Note on AV2: City or 'Online'
Note on AW2: Hosting partner
Note on AX2: e.g. Kick-off meeting
Note on AY2: Who attends
Note on AZ2: Calculated from the date, can be left empty
Note on BA2: Calculated from the date, can be left empty
Note on BB2: Optional: grouping in the Planning sheet, e.g. General Assembly (optional)

## configPlanning
Subtasks (optional) | [5 empty] | Risks (optional) | [5 empty] | KPIs (optional) |  |  |  | Communication KPIs (optional)
Task | Subtask | Milestones | Deliverables | Deadline | Responsible | ID | Description | WP | Likelihood | Severity | Mitigation | ID | Description | WP | Target | Channel | Target Groups | KPI
T1.1 | Organise the kick-off meeting and set up the governance bodies | MS1 |  | 1 | UCN | 1 | Delays in the delivery of sensor hardware | WP3, WP4 | Medium | High | Order components early and qualify a second supplier. | 1.1 | Water savings in pilot farms | WP4 | >= 20% | Project website | All | 1500 visitors per month
T1.1 | Prepare the project handbook with internal procedures |  | D1.1 | 3 | UCN | 2 | Low engagement of farmers in the pilots | WP2, WP4, WP5 | Medium | Medium | Involve farmer associations from the start and offer training. | 1.2 | Farmers using the decision-support platform | WP3, WP4 | >= 150 | Social media | Farmers, public | 8 posts per month
T1.1 | Coordinate periodic technical and financial reporting |  |  | 20 | UCN | 3 | Drought or extreme weather affecting the pilot season | WP4 | Low | High | Run pilots over two seasons and in several regions. | 2.1 | Farmers and advisors trained | WP5 | >= 500 | Scientific publications | Academic community | 6 open access
T2.1 | Run interviews and workshops with farmers in the pilot regions |  |  | 6 | EUFARM | 4 | Delay in submitting deliverables | WP1, WP2, WP3, WP4, WP5 | Low | Medium | Internal deadlines one month before the contractual due date.
T2.1 | Publish the stakeholder requirements report | MS2 | D2.1 | 8 | AGROLAB
Note on A2: Task number, e.g. T1.1 (required)
Note on B2: Description of the activity
Note on C2: Related milestones, e.g. MS1
Note on D2: Related deliverables, e.g. D1.1
Note on E2: Deadline month, e.g. 6
Note on F2: Responsible partner or person
Note on H2: Risk number
Note on I2: Description of the risk (required)
Note on J2: Work packages involved, e.g. WP1, WP2
Note on K2: Low, Medium or High
Note on L2: Low, Medium or High
Note on M2: Proposed risk-mitigation measures
Note on O2: KPI number, e.g. 1.1
Note on P2: Description of the indicator (required)
Note on Q2: Work package(s)
Note on R2: Target value
Note on T2: Communication channel (required)
Note on U2: Audience
Note on V2: Target value

## configDataVal (hidden)
DeliverableTypes | DisseminationLevel | RiskLevel | TrueFalse
R | PU | Low | TRUE
REPORT | SEN | Medium | FALSE
DEM | CO | High
DEC | CI
DATA | R-UE/EU-R
DMP | C-UE/EU-C
ORDP | S-UE/EU-S
ETHICS
SECURITY
OTHER